## Summary
RMS Project - Feature List Summary
Project Name: | Resource Management System (RMS)
Document Version: | 1.0
Date: | February 16, 2026
Phase 1 Timeline: | Feb 16 - March 2, 2026 (2 weeks)
Phase 1 Features: | 72
Phase 1 Story Points: | 404
Phase 2 Timeline: | Post March 2026 (TBD)
Phase 2 Features: | 12
Phase 2 Story Points: | TBD

## Phase 1 Features
Module | Feature ID | Feature Name | Description | Priority | Story Points | Dependencies | Acceptance Criteria | Status
Authentication & RBAC | AUTH-001 | User Login | Secure login with email and password | Critical | 8 | None | User can log in with valid credentials; Invalid login shows error; Session persists across refresh | Phase 1
Authentication & RBAC | AUTH-002 | Role-Based Access Control | Define Back Office and Admin roles with permission mapping | Critical | 12 | AUTH-001 | Recruiter sees recruiter menu; Admin sees admin menu; Permissions enforced at API level | Phase 1
Authentication & RBAC | AUTH-003 | Permission-Based Features | Restrict features based on user role | High | 8 | AUTH-002 | Recruiter cannot access Send to Client; Admin can process exits; All permissions tested | Phase 1
Authentication & RBAC | AUTH-004 | User Management | Admin CRUD for users | Medium | 6 | AUTH-002 | Admin creates Back Office user; New user can log in; Admin can deactivate users | Phase 1
Dashboard & Metrics | DASH-001 | Total Requests Metric | Display total number of resource requests | High | 4 | REQUEST-001 | Metric displays correct count; Updates when new request created | Phase 1
Dashboard & Metrics | DASH-002 | Onboarded Count | Display count of onboarded resources | High | 3 | ONBOARD-001 | Count matches manual query; Updates when resource onboarded | Phase 1
Dashboard & Metrics | DASH-003 | Awaiting Onboarding Count | Display count of candidates with client (awaiting onboarding) | High | 3 | ADMIN-006 | Shows Status = With Client count; Updates in real-time | Phase 1
Dashboard & Metrics | DASH-004 | To Be Shared Count | Display count of profiles with admin (to be shared with client) | High | 3 | PIPELINE-013 | Shows Status = With Admin count; Admin sees accurate count | Phase 1
Dashboard & Metrics | DASH-005 | Role-Wise Breakdown Chart | Bar/Pie chart showing distribution by role | Medium | 8 | JOBPROF-001 | Bar or pie chart displays; Tooltip shows exact count; Interactive | Phase 1
Dashboard & Metrics | DASH-006 | Technology Distribution Chart | Chart showing distribution by technology | Medium | 6 | JOBPROF-001 | Chart groups by technology; Interactive and responsive | Phase 1
Dashboard & Metrics | DASH-007 | Status Filter Dropdown | Filter dashboard by status | Medium | 4 | DASH-001 | Selecting status filters dashboard; Metrics update correctly | Phase 1
Dashboard & Metrics | DASH-008 | Attrition Rate Trend | Line graph showing exits over time | Low | 8 | EXIT-001 | Line graph shows exits over time; Trend line calculated | Phase 1
Dashboard & Metrics | DASH-009 | Avg Time to Onboard | Metric showing average days from request to onboarding | Low | 6 | ONBOARD-001 | Metric calculated correctly; Excludes rejected requests | Phase 1
Dashboard & Metrics | DASH-010 | Date Range Filter | Custom date range selection for dashboard | Low | 6 | DASH-001 | Custom date range selection; Accurate filtered data | Phase 1
Job Profile | JOBPROF-001 | Create Job Profile | Create job profile with role, technology, experience | High | 8 | None | Job profile created; Saved to database; Visible in list | Phase 1
Job Profile | JOBPROF-002 | Edit Job Profile | Edit existing job profile | High | 4 | JOBPROF-001 | Job profile edited; Changes saved; Updated in list | Phase 1
Job Profile | JOBPROF-003 | Delete Job Profile | Delete job profile with validation (cannot delete if linked) | Medium | 4 | JOBPROF-001 | Cannot delete if linked to requests; Confirmation dialog shown; Deletion successful | Phase 1
Job Profile | JOBPROF-004 | List Job Profiles | Paginated list of job profiles | High | 4 | JOBPROF-001 | Profiles listed; Pagination works; Search works | Phase 1
Job Profile | JOBPROF-005 | Duplicate Validation | Prevent duplicate role names | Medium | 3 | JOBPROF-001 | Same role name cannot be created twice; Error shown | Phase 1
Resource Request | REQUEST-001 | Create Request | Create resource request with auto-generated ID | Critical | 12 | JOBPROF-001 | Request ID auto-generated (REQ-YYYYMMDD-XXX); Job profile selected; Source captured; Priority set | Phase 1
Resource Request | REQUEST-002 | Job Profile Dropdown | Select job profile from dropdown when creating request | High | 4 | JOBPROF-001 | Dropdown populated from job profiles; Selection saved | Phase 1
Resource Request | REQUEST-003 | Request Source | Capture request source (Email/Chat) | Medium | 4 | REQUEST-001 | Source dropdown works; Email and Chat options available | Phase 1
Resource Request | REQUEST-004 | Priority Field | Set priority (Urgent/High/Medium/Low) | Medium | 3 | REQUEST-001 | Priority dropdown works; All 4 options available | Phase 1
Resource Request | REQUEST-005 | Multi-Position Support | Support requests for multiple positions | Medium | 6 | REQUEST-001 | Position count field works; Multiple candidates can be linked | Phase 1
Resource Request | REQUEST-006 | View Request List | Paginated list of all requests | High | 8 | REQUEST-001 | Requests listed; Pagination works; Sorting works | Phase 1
Resource Request | REQUEST-007 | Filter Requests | Multi-criteria filtering (status, priority, job profile) | Medium | 8 | REQUEST-006 | Filters work independently; Combined filters work; Reset filters works | Phase 1
Resource Request | REQUEST-008 | Search Requests | Search by request ID or candidate name | Medium | 6 | REQUEST-006 | Search by ID works; Search by name works; Partial match works | Phase 1
Recruiter Pipeline | PIPELINE-001 | Add Candidate (21 Fields) | Add candidate with complete 21-field form | Critical | 16 | REQUEST-001 | All 21 fields available; Validation works; Candidate saved | Phase 1
Recruiter Pipeline | PIPELINE-002 | Owner Assignment | Assign recruiter owner from dropdown | High | 4 | AUTH-001 | Owner dropdown populated; Selection saved | Phase 1
Recruiter Pipeline | PIPELINE-003 | Vendor Field | Capture sourcing vendor (WRS/GFM/Internal) | Medium | 3 | PIPELINE-001 | Vendor dropdown works; All 3 options available | Phase 1
Recruiter Pipeline | PIPELINE-004 | Interview DateTime | Date and time picker for interview | Medium | 4 | PIPELINE-001 | Date picker works; Time picker works; Saved correctly | Phase 1
Recruiter Pipeline | PIPELINE-005 | Candidate Status | Status dropdown with 9 options | High | 6 | PIPELINE-001 | All 9 statuses available; Status updates correctly | Phase 1
Recruiter Pipeline | PIPELINE-006 | CTC Fields | Current and Expected CTC fields | Medium | 3 | PIPELINE-001 | Numeric validation works; Both fields saved | Phase 1
Recruiter Pipeline | PIPELINE-007 | Location Fields | Current and Work Location fields | Low | 2 | PIPELINE-001 | Text fields work; Both locations saved | Phase 1
Recruiter Pipeline | PIPELINE-008 | Notice Period | Notice period in days | Low | 2 | PIPELINE-001 | Numeric field works; Validation (0-90 days) works | Phase 1
Recruiter Pipeline | PIPELINE-009 | Remarks Field | Multi-line text for notes | Low | 2 | PIPELINE-001 | Textarea works; Long text saved; Character limit enforced | Phase 1
Recruiter Pipeline | PIPELINE-010 | Resume Upload | Upload resume (PDF/DOCX, max 5MB) | Critical | 8 | PIPELINE-001 | File upload works; PDF and DOCX accepted; 5MB limit enforced; File stored | Phase 1
Recruiter Pipeline | PIPELINE-011 | Edit Candidate | Edit all 21 fields of existing candidate | High | 6 | PIPELINE-001 | All fields editable; Changes saved; Resume replaceable | Phase 1
Recruiter Pipeline | PIPELINE-012 | View Candidate List | View all candidates for a request | High | 8 | PIPELINE-001 | Candidates listed; All fields visible; Sorting works | Phase 1
Recruiter Pipeline | PIPELINE-013 | Mark With Admin | Update request status to With Admin | High | 4 | PIPELINE-001 | Status updates; Admin sees request; Request appears in admin queue | Phase 1
Admin Operations | ADMIN-001 | View With Admin | View all requests marked With Admin | High | 6 | PIPELINE-013 | List shows only With Admin requests; Pagination works | Phase 1
Admin Operations | ADMIN-002 | Validation Checklist | Checklist for email, format, JD alignment | Medium | 8 | ADMIN-001 | Checklist displays; Items can be checked/unchecked; Validation status saved | Phase 1
Admin Operations | ADMIN-003 | Download Profile | Download candidate profile as PDF | High | 4 | ADMIN-001 | PDF generated; Contains all candidate details; Resume included | Phase 1
Admin Operations | ADMIN-004 | Reject to Recruiter | Reject profile back to recruiter with reason | Medium | 6 | ADMIN-001 | Rejection reason captured; Status reverts; Recruiter notified | Phase 1
Admin Operations | ADMIN-005 | Generate Email Template | Auto-generate email for client submission | High | 8 | ADMIN-001 | Email template generated; Candidate details populated; Editable before send | Phase 1
Admin Operations | ADMIN-006 | Mark With Client | Update status to With Client after submission | High | 4 | ADMIN-005 | Status updates; Dashboard metrics update; Request appears in client queue | Phase 1
Admin Operations | ADMIN-007 | Log Communication | Log communication date, client contact, type | Medium | 6 | ADMIN-006 | Communication logged; Timestamp saved; Audit trail visible | Phase 1
Onboarding | ONBOARD-001 | Mark Onboarded | Mark candidate as onboarded with billing start date | Critical | 8 | ADMIN-006 | Billing date captured; Status updates to Onboarded; Dashboard updates | Phase 1
Onboarding | ONBOARD-002 | Client Email | Capture client email ID | High | 3 | ONBOARD-001 | Email field works; Email validation works; Saved correctly | Phase 1
Onboarding | ONBOARD-003 | Client Jira Username | Capture client Jira username | High | 3 | ONBOARD-001 | Text field works; Saved correctly | Phase 1
Onboarding | ONBOARD-004 | Update to Onboarded | Update status to Onboarded | High | 4 | ONBOARD-001 | Status updates; Visible in onboarded list; Dashboard updates | Phase 1
Onboarding | ONBOARD-005 | Client Rejection | Handle client rejection with reason | Medium | 6 | ADMIN-006 | Rejection reason captured; Status updates; Audit trail maintained | Phase 1
Onboarding | ONBOARD-006 | Replacement Required | Flag if replacement needed for rejection | Medium | 4 | ONBOARD-005 | Checkbox works; Flag saved; Used for backfill creation | Phase 1
Onboarding | ONBOARD-007 | Auto-Create Backfill | Auto-create backfill request on rejection if replacement needed | Medium | 8 | ONBOARD-006 | Backfill request created; Links to original; Inherits job profile | Phase 1
Exit Management | EXIT-001 | Process Exit | Capture exit reason and last working day | Critical | 8 | ONBOARD-001 | Exit form works; Reason captured; LWD captured; Status updates | Phase 1
Exit Management | EXIT-002 | Exit Reason Dropdown | 6 exit reason options | High | 4 | EXIT-001 | All 6 reasons available; Selection saved | Phase 1
Exit Management | EXIT-003 | Last Working Day | Date picker for LWD | High | 3 | EXIT-001 | Date picker works; Future dates allowed; Saved correctly | Phase 1
Exit Management | EXIT-004 | Exit Notes | Multi-line text for exit notes | Low | 2 | EXIT-001 | Textarea works; Long notes saved | Phase 1
Exit Management | EXIT-005 | Replacement Required (Exit) | Flag if replacement needed for exit | Medium | 4 | EXIT-001 | Checkbox works; Flag saved; Used for backfill | Phase 1
Exit Management | EXIT-006 | Auto-Create Backfill (Exit) | Auto-create backfill on exit if replacement needed | Medium | 6 | EXIT-005 | Backfill created; Links to original; Inherits job profile | Phase 1
Exit Management | EXIT-007 | Update to Exit | Update status to Exit | High | 3 | EXIT-001 | Status updates; Dashboard updates; Attrition metrics update | Phase 1
SOW Tracker | SOW-001 | Manual SOW Entry | Form to manually enter SOW details | Medium | 6 | None | SOW form works; All fields saved; Validation works | Phase 1
SOW Tracker | SOW-002 | Link to Requests | Link SOW to multiple request IDs | Medium | 6 | SOW-001 | Multi-select works; Request IDs linked; Association saved | Phase 1
SOW Tracker | SOW-003 | View SOW List | Table view of all SOWs | Medium | 6 | SOW-001 | SOWs listed; Pagination works; Sorting works | Phase 1
SOW Tracker | SOW-004 | Request Count per SOW | Display count of requests linked to each SOW | Low | 4 | SOW-002 | Count displayed correctly; Updates when requests linked/unlinked | Phase 1
Infrastructure | INFRA-001 | Supabase Setup | Create and configure Supabase project | Critical | 4 | None | Project created; Database provisioned; API keys generated | Phase 1
Infrastructure | INFRA-002 | Database Schema | Design and create 11 tables | Critical | 16 | INFRA-001 | All 11 tables created; Relationships defined; Constraints applied | Phase 1
Infrastructure | INFRA-003 | FastAPI Backend | Scaffold FastAPI backend with async architecture | Critical | 8 | INFRA-002 | FastAPI running; Async working; Database connected | Phase 1
Infrastructure | INFRA-004 | React Frontend | Setup React + Vite frontend | Critical | 6 | None | React app running; Routing works; API communication works | Phase 1
Infrastructure | INFRA-005 | API Endpoints | Define REST API structure | High | 8 | INFRA-003 | Endpoints documented; CRUD operations work; Error handling implemented | Phase 1
Infrastructure | INFRA-006 | CORS Configuration | Configure CORS for frontend-backend communication | Medium | 2 | INFRA-003 | CORS allows frontend domain; No CORS errors; Cookies work | Phase 1
Infrastructure | INFRA-007 | Environment Variables | Setup .env for secrets management | Medium | 3 | INFRA-003 | Env vars loaded; Secrets secured; No hardcoded credentials | Phase 1

## Phase 2 Features
Module | Feature ID | Feature Name | Description | Priority | Story Points | Dependencies | Acceptance Criteria | Status
Client Portal | PORTAL-001 | Client Login | Direct login for clients to view profiles | High | TBD | AUTH-001 | Client can log in; Sees only their requests; Cannot see other clients data | Phase 2
Client Portal | PORTAL-002 | Profile View & Feedback | Client can view profiles and provide feedback | High | TBD | PORTAL-001 | Profile details visible; Feedback form works; Admin notified | Phase 2
Advanced Analytics | ANALYTICS-001 | Predictive Attrition | ML model to predict attrition risk | Medium | TBD | EXIT-001 | Model trained; Risk score displayed; Recommendations shown | Phase 2
Advanced Analytics | ANALYTICS-002 | Custom Report Builder | Drag-and-drop report builder | Low | TBD | DASH-001 | Builder UI works; Custom reports generated; Export works | Phase 2
Integrations | INTEG-001 | Email Integration | Gmail/Outlook sync for request creation | Medium | TBD | REQUEST-001 | Emails synced; Requests auto-created; Attachments extracted | Phase 2
Integrations | INTEG-002 | Calendar Integration | Sync interview schedules to Google/Outlook calendar | Medium | TBD | PIPELINE-004 | Calendar events created; Reminders sent; Two-way sync works | Phase 2
Integrations | INTEG-003 | Jira API Integration | Sync onboarded resources to client Jira | High | TBD | ONBOARD-003 | Jira account auto-created; Username synced; Tickets created | Phase 2
Mobile App | MOBILE-001 | iOS App | Native iOS app for recruiters | Low | TBD | AUTH-001 | iOS app works; Login works; Core features accessible | Phase 2
Mobile App | MOBILE-002 | Android App | Native Android app for recruiters | Low | TBD | AUTH-001 | Android app works; Login works; Core features accessible | Phase 2
Advanced Features | ADV-001 | Bulk Upload | Excel import for candidates | Medium | TBD | PIPELINE-001 | Excel template works; Bulk import works; Validation on import | Phase 2
Advanced Features | ADV-002 | Document Version Control | Version history for resume uploads | Low | TBD | PIPELINE-010 | Versions tracked; Can revert to previous; Diff visible | Phase 2
Advanced Features | ADV-003 | Multi-Language Support | UI in multiple languages (English, Hindi) | Low | TBD | None | Language switcher works; All UI translated; Saves preference | Phase 2