## User Stories
Story ID | Title | As a... | I want to... | So that... | Acceptance Criteria | Priority | Epic | Sprint | Status
US-001 | Resource Request Creation | Back Office Recruiter | create resource requests with auto-generated IDs | I can track client requirements systematically | • Request ID auto-generated (REQ-YYYYMMDD-XXX) • Job profile selected from dropdown • Request source (Email/Chat) captured • Priority (Urgent/High/Medium/Low) can be set • Multi-position requests supported • Request saved and visible in list view | Critical | Resource Request Workflow | Sprint 2 | To Do
US-002 | Candidate Addition (21-Field Form) | Back Office Recruiter | add candidates with complete profiles | Admin can review all necessary information | • All 21 fields fillable (see PRD Section 4) • Resume uploadable (PDF/DOCX, max 5MB) • Owner (recruiter) assigned from dropdown • Status defaults to "New" • Candidate linked to request ID • Form validates required fields before save | Critical | Recruiter Pipeline | Sprint 3 | To Do
US-003 | Admin Profile Review | Admin | review recruiter-submitted profiles | I only send quality candidates to clients | • View all requests "With Admin" • See complete candidate profile with resume • Reject to recruiter with reason • Approve and proceed to client submission • Validation checklist visible (email, JD match, resume quality) • Track L1/L2 interview response status | Critical | Admin Operations | Sprint 4 | To Do
US-004 | Client Submission | Admin | generate professional emails for client submission | the process is standardized and auditable | • Email template auto-generated with candidate details • Can download candidate profile as PDF • Can log communication date and client contact • Status updates to "With Client" after submission • Audit trail maintained • Profile rejection flow handled (backfill yes/no) | Critical | Admin Operations | Sprint 4 | To Do
US-005 | Onboarding Workflow | Admin | capture onboarding details | billing and client systems are synchronized | • Mark candidate as onboarded • Billing start date captured • Client email ID captured • Client Jira username captured • Status updates to "Onboarded" • Dashboard metrics update in real-time | Critical | Lifecycle Management | Sprint 5 | To Do
US-006 | Exit Processing | Admin | process exits with reasons | attrition trends can be analyzed | • Select exit reason from dropdown (6 options: Better Offer, Personal, Performance, Client End, Project End, Other) • Last working day captured • Exit notes can be added • Replacement required flag can be set • Backfill request auto-created if replacement needed • Status updates to "Exit" | Critical | Lifecycle Management | Sprint 5 | To Do
US-007 | Dashboard Visibility | Management / Leadership | see real-time metrics | I can track pipeline health and make informed decisions | • Total requests count displayed • Onboarded count displayed • Awaiting onboarding count (status = "With Client") shown • To be shared count (status = "With Admin") shown • Role-wise breakdown chart displayed • Technology distribution visible • Resource status visible at each stage | High | Dashboard & Metrics | Sprint 6 | To Do
US-008 | SOW Tracker | Admin | track SOW details | headcount can be reconciled with contracts | • Manually enter SOW details • Link request IDs to SOW • View SOW list in table format (default: active SOWs) • See request count per SOW • Active SOW count = number of active resources • Filter by SOW status (Active/Expired/All) | Medium | Lifecycle Management | Sprint 5 | To Do
US-009 | Backfill Automation | Admin | have backfill requests auto-created | replacements are not forgotten when exits or rejections occur | • Backfill created when exit has "replacement required" = Yes • Backfill created when client rejection has "replacement required" = Yes • Backfill request inherits job profile from original • Backfill linked to original request ID | High | Lifecycle Management | Sprint 5 | To Do
US-010 | Communication Logging | Admin | log all client communications | there is a complete audit trail for compliance | • Log communication date • Log client contact person • Log communication type (email/call/meeting) • All logs timestamped and linked to request | Medium | Admin Operations | Sprint 4 | To Do

## Acceptance Criteria Matrix
Story ID | Criteria # | Acceptance Criterion | Testable? | Automation Priority
US-001 | AC-01 | Request ID auto-generated (REQ-YYYYMMDD-XXX) | Yes | E2E
US-001 | AC-02 | Job profile selected from dropdown | Yes | E2E
US-001 | AC-03 | Request source (Email/Chat) captured | Yes | E2E
US-001 | AC-04 | Priority (Urgent/High/Medium/Low) can be set | Yes | E2E
US-001 | AC-05 | Multi-position requests supported | Yes | E2E
US-001 | AC-06 | Request saved and visible in list view | Yes | E2E
US-002 | AC-01 | All 21 fields fillable (see PRD Section 4) | Yes | E2E
US-002 | AC-02 | Resume uploadable (PDF/DOCX, max 5MB) | Yes | E2E
US-002 | AC-03 | Owner (recruiter) assigned from dropdown | Yes | E2E
US-002 | AC-04 | Status defaults to "New" | Yes | E2E
US-002 | AC-05 | Candidate linked to request ID | Yes | E2E
US-002 | AC-06 | Form validates required fields before save | Yes | E2E
US-003 | AC-01 | View all requests "With Admin" | Yes | E2E
US-003 | AC-02 | See complete candidate profile with resume | Yes | E2E
US-003 | AC-03 | Reject to recruiter with reason | Yes | E2E
US-003 | AC-04 | Approve and proceed to client submission | Yes | E2E
US-003 | AC-05 | Validation checklist visible (email, JD match, resume quality) | Yes | E2E
US-003 | AC-06 | Track L1/L2 interview response status | Yes | E2E
US-004 | AC-01 | Email template auto-generated with candidate details | Yes | E2E
US-004 | AC-02 | Can download candidate profile as PDF | Yes | E2E
US-004 | AC-03 | Can log communication date and client contact | Yes | E2E
US-004 | AC-04 | Status updates to "With Client" after submission | Yes | E2E
US-004 | AC-05 | Audit trail maintained | Yes | E2E
US-004 | AC-06 | Profile rejection flow handled (backfill yes/no) | Yes | E2E
US-005 | AC-01 | Mark candidate as onboarded | Yes | E2E
US-005 | AC-02 | Billing start date captured | Yes | E2E
US-005 | AC-03 | Client email ID captured | Yes | E2E
US-005 | AC-04 | Client Jira username captured | Yes | E2E
US-005 | AC-05 | Status updates to "Onboarded" | Yes | E2E
US-005 | AC-06 | Dashboard metrics update in real-time | Yes | E2E
US-006 | AC-01 | Select exit reason from dropdown (6 options: Better Offer, Personal, Performance, Client End, Project End, Other) | Yes | E2E
US-006 | AC-02 | Last working day captured | Yes | E2E
US-006 | AC-03 | Exit notes can be added | Yes | E2E
US-006 | AC-04 | Replacement required flag can be set | Yes | E2E
US-006 | AC-05 | Backfill request auto-created if replacement needed | Yes | E2E
US-006 | AC-06 | Status updates to "Exit" | Yes | E2E
US-007 | AC-01 | Total requests count displayed | Yes | E2E
US-007 | AC-02 | Onboarded count displayed | Yes | E2E
US-007 | AC-03 | Awaiting onboarding count (status = "With Client") shown | Yes | E2E
US-007 | AC-04 | To be shared count (status = "With Admin") shown | Yes | E2E
US-007 | AC-05 | Role-wise breakdown chart displayed | Yes | E2E
US-007 | AC-06 | Technology distribution visible | Yes | E2E
US-007 | AC-07 | Resource status visible at each stage | Yes | E2E
US-008 | AC-01 | Manually enter SOW details | Yes | E2E
US-008 | AC-02 | Link request IDs to SOW | Yes | E2E
US-008 | AC-03 | View SOW list in table format (default: active SOWs) | Yes | E2E
US-008 | AC-04 | See request count per SOW | Yes | E2E
US-008 | AC-05 | Active SOW count = number of active resources | Yes | E2E
US-008 | AC-06 | Filter by SOW status (Active/Expired/All) | Yes | E2E
US-009 | AC-01 | Backfill created when exit has "replacement required" = Yes | Yes | E2E
US-009 | AC-02 | Backfill created when client rejection has "replacement required" = Yes | Yes | E2E
US-009 | AC-03 | Backfill request inherits job profile from original | Yes | E2E
US-009 | AC-04 | Backfill linked to original request ID | Yes | E2E
US-010 | AC-01 | Log communication date | Yes | E2E
US-010 | AC-02 | Log client contact person | Yes | E2E
US-010 | AC-03 | Log communication type (email/call/meeting) | Yes | E2E
US-010 | AC-04 | All logs timestamped and linked to request | Yes | E2E