## Summary
RMS Project — Feature List v2.0
Updated: March 2, 2026 ¦ Phase 1 Complete ✅ ¦ Demo: Feb 23, 2026
Project Name: | Resource Management System (RMS)
Document Version: | 2.0 (Updated)
Original Version: | 1.0 — February 16, 2026 — Jaicind Santhibhavan
Update Date: | March 2, 2026
Phase 1 Timeline: | Feb 16 – March 2, 2026 (2 weeks) ✅ DELIVERED
Phase 1 Features: | 75 (72 original + 3 added)
Phase 1 Status: | ✅ All Done — Demoed to Raja PV & Senthil Natarajan on Feb 23, 2026
Phase 1 E2E Tests: | 17 flows verified via Playwright
Phase 2 Timeline: | Post March 2026 (TBD)
Phase 2 Features: | 20 (12 original + 8 new)
Phase 2 Story Points: | TBD
Tech Stack (Actual): | FastAPI + React 18 + TypeScript + Supabase (PostgreSQL)
Auth: | Supabase Auth (JWT, ES256)
Storage: | Supabase Storage (resume uploads)
DB Tables (Actual): | 6 — profiles, job_profiles, resource_requests, candidates, communication_logs, sows
API Endpoints: | 23

## Phase 1 Features
Module | Feature ID | Feature Name | Description | Priority | Story Points | Dependencies | Acceptance Criteria | Status
Authentication & RBAC | AUTH-001 | User Login | Secure login with email and password via Supabase Auth | Critical | 8 | None | User can log in with valid credentials; Invalid login shows error; Session persists across refresh | ✅ Done
Authentication & RBAC | AUTH-002 | Role-Based Access Control | Three roles: ADMIN, RECRUITER, MANAGEMENT with permission mapping | Critical | 12 | AUTH-001 | Recruiter sees recruiter menu; Admin sees admin menu; Management sees dashboards; Permissions enforced at API level | ✅ Done
Authentication & RBAC | AUTH-003 | Permission-Based Features | Restrict features based on user role | High | 8 | AUTH-002 | Recruiter cannot access Send to Client; Admin can process exits; Management has read-only | ✅ Done
Authentication & RBAC | AUTH-004 | User Management | Admin CRUD for user accounts | Medium | 6 | AUTH-002 | Admin creates user; New user can log in; Admin can deactivate users | ✅ Done
Dashboard & Metrics | DASH-001 | Total Requests Metric | Display total number of resource requests | High | 4 | REQUEST-001 | Metric displays correct count; Updates when new request created | ✅ Done
Dashboard & Metrics | DASH-002 | Onboarded Count | Display count of onboarded resources | High | 3 | ONBOARD-001 | Count matches DB query; Updates when resource onboarded | ✅ Done
Dashboard & Metrics | DASH-003 | Awaiting Onboarding Count | Display count of candidates With Client (awaiting onboarding) | High | 3 | ADMIN-006 | Shows Status = WITH_CLIENT count; Updates in real-time | ✅ Done
Dashboard & Metrics | DASH-004 | To Be Shared Count | Display count of profiles With Admin (to be shared with client) | High | 3 | PIPELINE-013 | Shows Status = With Admin count; Admin sees accurate count | ✅ Done
Dashboard & Metrics | DASH-005 | Role-Wise Breakdown Chart | Bar/Pie chart showing distribution by role | Medium | 8 | JOBPROF-001 | Chart displays; Tooltip shows exact count; Interactive | ✅ Done
Dashboard & Metrics | DASH-006 | Technology Distribution Chart | Chart showing distribution by technology | Medium | 6 | JOBPROF-001 | Chart groups by technology; Interactive and responsive | ✅ Done
Dashboard & Metrics | DASH-007 | Status Filter Dropdown | Filter dashboard by status | Medium | 4 | DASH-001 | Selecting status filters dashboard; Metrics update correctly | ✅ Done
Dashboard & Metrics | DASH-008 | Attrition Rate Trend | Line graph showing exits over time | Low | 8 | EXIT-001 | Line graph shows exits over time; Trend line calculated | ✅ Done
Dashboard & Metrics | DASH-009 | Avg Time to Onboard | Metric showing average days from request to onboarding | Low | 6 | ONBOARD-001 | Metric calculated correctly; Excludes rejected requests | ✅ Done
Dashboard & Metrics | DASH-010 | Date Range Filter | Custom date range selection for dashboard | Low | 6 | DASH-001 | Custom date range selection; Accurate filtered data | ✅ Done
Job Profile | JOBPROF-001 | Create Job Profile | Create job profile with role, technology, experience | High | 8 | None | Job profile created; Saved to database; Visible in list | ✅ Done
Job Profile | JOBPROF-002 | Edit Job Profile | Edit existing job profile | High | 4 | JOBPROF-001 | Job profile edited; Changes saved; Updated in list | ✅ Done
Job Profile | JOBPROF-003 | Delete Job Profile | Delete job profile with validation (cannot delete if linked) | Medium | 4 | JOBPROF-001 | Cannot delete if linked to requests; Confirmation dialog; Deletion successful | ✅ Done
Job Profile | JOBPROF-004 | List Job Profiles | Paginated list of job profiles | High | 4 | JOBPROF-001 | Profiles listed; Pagination works; Search works | ✅ Done
Job Profile | JOBPROF-005 | Duplicate Validation | Prevent duplicate role names | Medium | 3 | JOBPROF-001 | Same role name cannot be created twice; Error shown | ✅ Done
Resource Request | REQUEST-001 | Create Request | Create resource request with auto-generated ID (REQ-YYYYMMDD-XXX) | Critical | 12 | JOBPROF-001 | Request ID auto-generated; Job profile selected; Source captured; Priority set | ✅ Done
Resource Request | REQUEST-002 | Job Profile Dropdown | Select job profile from dropdown when creating request | High | 4 | JOBPROF-001 | Dropdown populated from job profiles; Selection saved | ✅ Done
Resource Request | REQUEST-003 | Request Source | Capture request source (Email/Chat) | Medium | 4 | REQUEST-001 | Source dropdown works; Email and Chat options available | ✅ Done
Resource Request | REQUEST-004 | Priority Field | Set priority (Urgent/High/Medium/Low) | Medium | 3 | REQUEST-001 | Priority dropdown works; All 4 options available | ✅ Done
Resource Request | REQUEST-005 | Multi-Position Support | Support requests for multiple positions | Medium | 6 | REQUEST-001 | Position count field works; Multiple candidates can be linked | ✅ Done
Resource Request | REQUEST-006 | View Request List | Paginated list of all requests | High | 8 | REQUEST-001 | Requests listed; Pagination works; Sorting works | ✅ Done
Resource Request | REQUEST-007 | Filter Requests | Multi-criteria filtering (status, priority, job profile) | Medium | 8 | REQUEST-006 | Filters work independently; Combined filters work; Reset filters works | ✅ Done
Resource Request | REQUEST-008 | Search Requests | Search by request ID or candidate name | Medium | 6 | REQUEST-006 | Search by ID works; Search by name works; Partial match works | ✅ Done
Recruiter Pipeline | PIPELINE-001 | Add Candidate (21 Fields) | Add candidate with complete 21-field form | Critical | 16 | REQUEST-001 | All 21 fields available; Validation works; Candidate saved | ✅ Done
Recruiter Pipeline | PIPELINE-002 | Owner Assignment | Assign recruiter owner from dropdown | High | 4 | AUTH-001 | Owner dropdown populated; Selection saved | ✅ Done
Recruiter Pipeline | PIPELINE-003 | Vendor Field | Capture sourcing vendor from vendor master | Medium | 3 | PIPELINE-001 | Vendor dropdown populated from master; Selection saved | ✅ Done
Recruiter Pipeline | PIPELINE-004 | Interview DateTime | Date and time picker for interview | Medium | 4 | PIPELINE-001 | Date picker works; Time picker works; Saved correctly | ✅ Done
Recruiter Pipeline | PIPELINE-005 | Candidate Status (HR-Approved) | HR-approved status dropdown: NEW, SCREENING_DONE, L1_COMPLETED, L1_REJECTED, L2_COMPLETED, L2_REJECTED, SELECTED, WITH_CLIENT, ONBOARDED, EXIT | High | 6 | PIPELINE-001 | All 10 HR-approved statuses available; Status updates correctly; No legacy statuses | ✅ Done
Recruiter Pipeline | PIPELINE-006 | CTC Fields | Current and Expected CTC fields | Medium | 3 | PIPELINE-001 | Numeric validation works; Both fields saved | ✅ Done
Recruiter Pipeline | PIPELINE-007 | Location Fields | Current and Work Location fields | Low | 2 | PIPELINE-001 | Text fields work; Both locations saved | ✅ Done
Recruiter Pipeline | PIPELINE-008 | Notice Period | Notice period in days (0–90) | Low | 2 | PIPELINE-001 | Numeric field works; Validation works | ✅ Done
Recruiter Pipeline | PIPELINE-009 | Remarks Field | Multi-line text for notes (max 1000 chars) | Low | 2 | PIPELINE-001 | Textarea works; Long text saved; Character limit enforced | ✅ Done
Recruiter Pipeline | PIPELINE-010 | Resume Upload | Upload resume to Supabase Storage (PDF/DOCX, max 5MB) | Critical | 8 | PIPELINE-001 | File upload works; PDF and DOCX accepted; 5MB limit enforced; File stored in Supabase | ✅ Done
Recruiter Pipeline | PIPELINE-011 | Edit Candidate | Edit all 21 fields of existing candidate | High | 6 | PIPELINE-001 | All fields editable; Changes saved; Resume replaceable | ✅ Done
Recruiter Pipeline | PIPELINE-012 | View Candidate List | View all candidates for a request | High | 8 | PIPELINE-001 | Candidates listed; All fields visible; Sorting works | ✅ Done
Recruiter Pipeline | PIPELINE-013 | Mark With Admin | Update request status to With Admin | High | 4 | PIPELINE-001 | Status updates; Admin sees request; Request appears in admin queue | ✅ Done
Admin Operations | ADMIN-001 | View With Admin | View all requests marked With Admin | High | 6 | PIPELINE-013 | List shows only With Admin requests; Pagination works | ✅ Done
Admin Operations | ADMIN-002 | Validation Checklist | Checklist for email, format, JD alignment | Medium | 8 | ADMIN-001 | Checklist displays; Items can be checked/unchecked; Validation status saved | ✅ Done
Admin Operations | ADMIN-003 | Download Profile | Download candidate profile as PDF | High | 4 | ADMIN-001 | PDF generated; Contains all candidate details; Resume included | ✅ Done
Admin Operations | ADMIN-004 | Reject to Recruiter | Reject profile back to recruiter with reason | Medium | 6 | ADMIN-001 | Rejection reason captured; Status reverts; Recruiter notified | ✅ Done
Admin Operations | ADMIN-005 | Generate Email Template | Auto-generate email for client submission | High | 8 | ADMIN-001 | Email template generated; Candidate details populated; Editable before send | ✅ Done
Admin Operations | ADMIN-006 | Mark With Client | Update status to With Client after submission | High | 4 | ADMIN-005 | Status updates; Dashboard metrics update; Request moves to client queue | ✅ Done
Admin Operations | ADMIN-007 | Log Communication | Log communication date, client contact, type | Medium | 6 | ADMIN-006 | Communication logged; Timestamp saved; Audit trail visible | ✅ Done
Onboarding | ONBOARD-001 | Mark Onboarded | Mark candidate as onboarded with billing start date | Critical | 8 | ADMIN-006 | Billing date captured; Status updates to ONBOARDED; Dashboard updates | ✅ Done
Onboarding | ONBOARD-002 | Client Email | Capture client email ID on onboarding | High | 3 | ONBOARD-001 | Email field works; Email validation works; Saved correctly | ✅ Done
Onboarding | ONBOARD-003 | Client Jira Username | Capture client Jira username on onboarding | High | 3 | ONBOARD-001 | Text field works; Saved correctly; Mapped for billing | ✅ Done
Onboarding | ONBOARD-004 | Update to Onboarded | Update candidate status to ONBOARDED | High | 4 | ONBOARD-001 | Status updates; Visible in onboarded list; Dashboard updates | ✅ Done
Onboarding | ONBOARD-005 | Client Rejection | Handle client rejection with reason | Medium | 6 | ADMIN-006 | Rejection reason captured; Status updates; Audit trail maintained | ✅ Done
Onboarding | ONBOARD-006 | Replacement Required | Flag if replacement needed on client rejection | Medium | 4 | ONBOARD-005 | Checkbox works; Flag saved; Used for backfill creation | ✅ Done
Onboarding | ONBOARD-007 | Auto-Create Backfill (Rejection) | Auto-create backfill request on client rejection if replacement needed | Medium | 8 | ONBOARD-006 | Backfill request created; Links to original; Inherits job profile; Same SOW carries forward | ✅ Done
Exit Management | EXIT-001 | Process Exit | Capture exit reason and last working day | Critical | 8 | ONBOARD-001 | Exit form works; Reason captured; LWD captured; Status updates to EXIT | ✅ Done
Exit Management | EXIT-002 | Exit Reason Dropdown | 6 exit reason options: Better Offer, Personal, Performance, Client End, Project End, Other | High | 4 | EXIT-001 | All 6 reasons available; Selection saved | ✅ Done
Exit Management | EXIT-003 | Last Working Day | Date picker for last working day | High | 3 | EXIT-001 | Date picker works; Saved correctly | ✅ Done
Exit Management | EXIT-004 | Exit Notes | Multi-line text for exit notes | Low | 2 | EXIT-001 | Textarea works; Long notes saved | ✅ Done
Exit Management | EXIT-005 | Replacement Required (Exit) | Flag if replacement needed on exit | Medium | 4 | EXIT-001 | Checkbox works; Flag saved; Triggers backfill if Yes | ✅ Done
Exit Management | EXIT-006 | Auto-Create Backfill (Exit) | Auto-create backfill on exit if replacement needed; same SOW carries forward | Medium | 6 | EXIT-005 | Backfill created; Links to original; Inherits job profile; Same SOW; overlap_until date captured | ✅ Done
Exit Management | EXIT-007 | Update to Exit | Update candidate status to EXIT | High | 3 | EXIT-001 | Status updates; Dashboard updates; Attrition metrics update | ✅ Done
SOW Tracker | SOW-001 | Manual SOW Entry | Form to manually enter SOW details (Admin only) | Medium | 6 | None | SOW form works; All fields saved; Validation works | ✅ Done
SOW Tracker | SOW-002 | Link SOW to Requests | SOW is mandatory-linked to each resource request | Medium | 6 | SOW-001 | SOW selection required on request creation; Association saved; Validated at API level | ✅ Done
SOW Tracker | SOW-003 | View SOW List (Active Default) | Table view of all SOWs — default filter = Active SOWs only | Medium | 6 | SOW-001 | Active SOWs shown by default; Filter to show inactive/all works; Pagination works | ✅ Done
SOW Tracker | SOW-004 | Request Count per SOW | Display count of requests and onboarded resources per SOW | Low | 4 | SOW-002 | Linked request count displayed; Onboarded instances count correct; Updates on change | ✅ Done
Infrastructure | INFRA-001 | Supabase Setup | Create and configure Supabase project with PostgreSQL + Auth + Storage | Critical | 4 | None | Project created; Database provisioned; Auth configured; Storage bucket active | ✅ Done
Infrastructure | INFRA-002 | Database Schema (6 Tables) | Design and create 6 tables: profiles, job_profiles, resource_requests, candidates, communication_logs, sows | Critical | 16 | INFRA-001 | All 6 tables created; Relationships defined; Constraints applied; RLS policies set | ✅ Done
Infrastructure | INFRA-003 | FastAPI Backend (Async) | Scaffold FastAPI backend with async architecture (23 endpoints) | Critical | 8 | INFRA-002 | FastAPI running on Uvicorn; Async operations working; Supabase connected; 23 endpoints live | ✅ Done
Infrastructure | INFRA-004 | React Frontend | Setup React 18 + TypeScript + Vite frontend | Critical | 6 | None | React app running; Routing works; API communication works; TypeScript types clean | ✅ Done
Infrastructure | INFRA-005 | API Endpoints (23) | Define and implement 23 REST API endpoints | High | 8 | INFRA-003 | All endpoints documented; CRUD operations work; Error handling implemented; Auth guards active | ✅ Done
Infrastructure | INFRA-006 | CORS Configuration | Configure CORS for frontend-backend communication | Medium | 2 | INFRA-003 | CORS allows frontend domain; No CORS errors in browser | ✅ Done
Infrastructure | INFRA-007 | Environment Variables | Setup .env for secrets management | Medium | 3 | INFRA-003 | Env vars loaded; Secrets secured; No hardcoded credentials | ✅ Done
Vendor Management | F-073 | Vendor Management Module | CRUD module for vendor master — WRS, GFM, Internal, Anton vendors. Admin-only write access. Vendor master drives dropdown across candidate forms and dashboard analytics. | High | 8 | AUTH-002, PIPELINE-003 | Admin can add/edit/deactivate vendors; Vendor dropdown in candidate form pulls from master; Vendor sourcing analytics reflected in dashboard | ✅ Done
Recruiter Pipeline | F-074 | Kanban View — Candidate Pipeline | Visual Kanban board grouping candidates by pipeline status column. Supports drag-to-update status. Provides at-a-glance view of all candidates across stages. | High | 10 | PIPELINE-001, PIPELINE-005 | Kanban board renders all pipeline status columns; Candidates appear in correct column; Column counts accurate; Responsive layout | ✅ Done
Recruiter Pipeline | F-075 | L1/L2 Interview Feedback Capture | Dedicated fields on candidate record to capture L1 and L2 round-specific interview feedback and outcomes. Feeds into status transitions (L1_COMPLETED, L1_REJECTED, L2_COMPLETED, L2_REJECTED). | High | 6 | PIPELINE-001, PIPELINE-005 | L1 feedback field available; L2 feedback field available; Feedback saved on candidate record; Status correctly transitions to L1/L2 outcomes | ✅ Done

## Phase 2 Features
Module | Feature ID | Feature Name | Description | Priority | Story Points | Dependencies | Acceptance Criteria | Status
Client Portal | PORTAL-001 | Client Login | Direct login for clients to view their request profiles | High | TBD | AUTH-001 | Client can log in; Sees only their requests; Cannot see other clients data | Phase 2 — Planned
Client Portal | PORTAL-002 | Profile View & Feedback | Client can view candidate profiles and provide accept/reject feedback | High | TBD | PORTAL-001 | Profile details visible; Feedback form works; Admin notified | Phase 2 — Planned
Advanced Analytics | ANALYTICS-001 | Predictive Attrition | ML-based model to predict attrition risk for onboarded resources | Medium | TBD | EXIT-001 | Model trained; Risk score displayed; Recommendations shown | Phase 2 — Planned
Advanced Analytics | ANALYTICS-002 | Custom Report Builder | Drag-and-drop custom report builder with export to PDF | Low | TBD | DASH-001 | Builder UI works; Custom reports generated; Export works | Phase 2 — Planned
Integrations | INTEG-001 | Email Integration | Gmail/Outlook sync for automated request creation from emails | Medium | TBD | REQUEST-001 | Emails synced; Requests auto-created; Attachments extracted | Phase 2 — Planned
Integrations | INTEG-002 | Calendar Integration | Sync interview schedules to Google/Outlook calendar | Medium | TBD | PIPELINE-004 | Calendar events created; Reminders sent; Two-way sync works | Phase 2 — Planned
Integrations | INTEG-003 | Jira API Integration | Sync onboarded resources to client Jira (pending client approval for API access) | High | TBD | ONBOARD-003 | Jira account auto-created; Username synced; Tickets created | Phase 2 — Planned
Mobile App | MOBILE-001 | iOS App | Native iOS app for recruiters and admins | Low | TBD | AUTH-001 | iOS app works; Login works; Core features accessible | Phase 2 — Planned
Mobile App | MOBILE-002 | Android App | Native Android app for recruiters and admins | Low | TBD | AUTH-001 | Android app works; Login works; Core features accessible | Phase 2 — Planned
Advanced Features | ADV-001 | Bulk Upload | Excel import for candidate batch onboarding | Medium | TBD | PIPELINE-001 | Excel template works; Bulk import works; Validation on import | Phase 2 — Planned
Advanced Features | ADV-002 | Document Version Control | Version history for resume uploads | Low | TBD | PIPELINE-010 | Versions tracked; Can revert to previous; Diff visible | Phase 2 — Planned
Advanced Features | ADV-003 | Multi-Language Support | UI in multiple languages (English, Hindi) | Low | TBD | None | Language switcher works; All UI translated; Saves preference | Phase 2 — Planned
Payroll Management | F-P2-013 | Payroll Management — Jira Dump Import | Import Jira time tracking CSV exports and calculate payroll for onboarded resources. Client will not allow direct Jira API access — HR team provides monthly CSV dumps. System calculates billable hours × rate and generates payroll records. | High | TBD | ONBOARD-001 | CSV upload works; Jira hours mapped to correct resources; Payroll calculation correct; Summary report generated; Export to Excel/PDF | Phase 2 — Planned
Exit Management | F-P2-014 | Exit Management Full Flow (Dedicated Page) | Dedicated Exit Management page with full exit workflow: initiation, reason capture, LWD, replacement decision, overlap tracking, and exit analytics. Phase 1 implements basic exit within candidate record; this is a dedicated full-flow page. | High | TBD | EXIT-001 | Dedicated exit page renders; All exit fields available; Replacement workflow complete; Exit analytics dashboard shows attrition trends | Phase 2 — Planned
Onboarding | F-P2-015 | Onboarding Workflow Page | Dedicated Onboarding Workflow page for structured onboarding: billing date capture, client Jira ID assignment, onboarding checklist, and documentation tracking. Extends basic onboarding fields from Phase 1. | High | TBD | ONBOARD-001 | Dedicated onboarding page renders; Checklist available; Billing date and Jira ID captured; Onboarding status tracked; Notification sent on completion | Phase 2 — Planned
Infrastructure | F-P2-016 | Production Hosting & Deployment | Deploy the full RMS stack to a production cloud environment (Railway/Fly.io or equivalent). Includes CI/CD pipeline, HTTPS, custom domain, and environment separation (dev/prod). | Critical | TBD | INFRA-001 | App accessible via HTTPS on production URL; Zero-downtime deployment; CI/CD pipeline runs on push; Prod DB separate from dev | Phase 2 — Planned
Infrastructure | F-P2-017 | PR Review Workflow Setup | Configure GitHub branch protection rules and PR review workflow per Jaicind's process: daily commits → PR creation → manager approval → merge to main. Includes required reviews and status check gates. | High | TBD | INFRA-004 | Branch protection enabled on main; PRs require at least 1 reviewer approval; Status checks must pass; Direct push to main blocked; Workflow documented | Phase 2 — Planned
Documentation & Training | F-P2-018 | User Training Materials | Create user-facing training materials: SOPs for Back Office Recruiters and Admins, video walkthroughs of key flows, quick reference cards, and FAQ document. | High | TBD | None | Recruiter SOP document complete; Admin SOP document complete; At least 3 key workflow videos recorded; Quick reference cards printed; FAQ answers 20+ questions | Phase 2 — Planned
AI Features | F-P2-019 | Resume Parsing (AI-Powered) | AI-powered extraction of candidate details from uploaded PDF/DOCX resumes. Auto-populate candidate form fields (name, email, skills, experience, current company) from resume content to reduce manual entry. | Medium | TBD | PIPELINE-010 | Resume parsed on upload; Name, email, skills auto-populated; Accuracy ≥ 80% on standard formats; User can override any populated field | Phase 2 — Planned
Integrations | F-P2-020 | LinkedIn / Job Board API Integration | Integration with LinkedIn and/or third-party job boards for direct candidate sourcing into the RMS pipeline. Mentioned by Senthil Natarajan in stakeholder call. Reduces time spent on manual candidate entry from job boards. | Medium | TBD | PIPELINE-001 | LinkedIn profile import works; Job board search integrated; Candidate pre-filled from public profile; Duplicate detection works | Phase 2 — Planned

## Change Log
Feature List — Change Log
Date | Change | Details | Author
Feb 16, 2026 | v1.0 Created | Initial feature list: 72 Phase 1 features, 12 Phase 2 features | Jaicind Santhibhavan
Mar 2, 2026 | v2.0 Update — Phase 1 Status | All 72 Phase 1 features marked ✅ Done. Phase 1 delivered on time. Demo to Raja PV and Senthil Natarajan on Feb 23, 2026. | Parth P
Mar 2, 2026 | v2.0 Update — New P1 Features | Added F-073 (Vendor Management Module), F-074 (Kanban View), F-075 (L1/L2 Interview Feedback) — built but not in original list. | Parth P
Mar 2, 2026 | v2.0 Update — Phase 2 Expanded | Added 8 new Phase 2 items: F-P2-013 (Payroll/Jira), F-P2-014 (Exit Full Flow), F-P2-015 (Onboarding Workflow), F-P2-016 (Production Hosting), F-P2-017 (PR Review), F-P2-018 (Training), F-P2-019 (Resume AI), F-P2-020 (LinkedIn API). New items highlighted in blue. | Parth P
Mar 2, 2026 | v2.0 Update — Candidate Statuses | Updated PIPELINE-005 to reflect 10 HR-approved statuses: NEW, SCREENING_DONE, L1_COMPLETED, L1_REJECTED, L2_COMPLETED, L2_REJECTED, SELECTED, WITH_CLIENT, ONBOARDED, EXIT (supersedes legacy v1.0 statuses). | Parth P
Mar 2, 2026 | v2.0 Update — Infrastructure | Updated INFRA-002 description: actual DB is 6 tables (not 11 as projected in v1.0). Updated INFRA-003/005 to reflect actual 23 endpoints. | Parth P